## NamNH15
# | Ngày | Người đảm nhiệm | Nội dung công việc | Tiến độ | Status | Plan Start Date | Plan End Date | Note/Nơi lưu report
1 | 20140403 | NamNH15 | Đọc Specs & Requirement | 100% | Done | 20140402 | 20140403 | N/A
2 | 20140403 | NamNH15 | Log Q&A |  |  | 20140402 |  | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Q&A List/Fr-HN29n_Group1_Q-A list.xls
3 | 20140403 | NamNH15 | Tạo screen desgin cho UC1 và UC28 | 100% | Done | 20140403 | 20140403 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/ScreenDesign/ScreenDesign.xlsx
4 | 20140403 | NamNH15 | Tạo database design cho UC1 và UC28 | 70% | In Progress | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/DatabaseDiagram/G1_DatabaseDiagram.jpg
5 | 20140404 | NamNH15 | Tạo class diagram cho UC1 và UC 28 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/ClassDiagram/FR-HN29n_G1_ClassDiagram.xlsx
6 | 20140404 | NamNH15 | Tạo sequencediagram cho UC1 và UC28 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/SequenceDiagram/FR-HN29n_G1_SequenceDiagram.xlsx
7 | 20140407 | NamNH15 | Tạo Unit test cho UC1 và 1 phần của UC 28 | 70% | In Progress | 20140407 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/NamNH15
8 | 20140408 | NamNH15 | Tạo Unit test cho UC28 và hoàn thiện Unit test | 100% | Done | 20140408 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/NamNH15
9 | 20140408 | NamNH15 | Review Unit Test | 100% | Done | 20140408 | 20140408 | N/A
10 | 20140408 | NamNH15 | Coding cho trang HomePage | 20% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
11 | 20140410 | NamNH15 | Coding cho UC1 và UC28 | 70% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
12 | 20140411 | NamNH15 | Coding cho UC1 và UC28 | 85% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1

## ThaoLTT
# | Ngày | Người đảm nhiệm | Nội dung công việc | Tiến độ | Status | Plan Start Date | Plan End Date | Note/Nơi lưu report
1 | 20140403 | ThaoLTT | Đọc Specs & Requirement | 100% | Done | 20140402 | 20140403 | N/A
2 | 20140403 | ThaoLTT | Log Q&A |  |  | 20140402 |  | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Q&A List/Fr-HN29n_Group1_Q-A list.xls
3 | 20140403 | ThaoLTT | Tạo screen desgin cho UC29,UC30,UC,31,UC32 | 100% | Done | 20140403 | 20140403 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/ScreenDesign/ScreenDesign.xlsx
4 | 20140403 | ThaoLTT | Tạo database design cho UC29,UC30,UC,31,UC32 | 60% | In Progress | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/DatabaseDiagram/G1_DatabaseDiagram.jpg
5 | 20140404 | ThaoLTT | Tạo class diagram cho UC29,UC30,UC31,UC32 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/ClassDiagram/FR-HN29n_G1_ClassDiagram.xlsx
6 | 20140404 | ThaoLTT | Tạo sequencediagram cho UC29,UC30,UC31,UC32 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/SequenceDiagram/FR-HN29n_G1_SequenceDiagram.xlsx
7 | 20140404 | ThaoLTT | Tạo Database trên server | 50% | In Progress | 20140404 | 20140407 | 10.16.102.17
8 | 20140407 | ThaoLTT | Tạo Database trên server | 100% | Done | 20140404 | 20140407 | 10.16.102.17
9 | 20140407 | ThaoLTT | Tạo Unit Test Cho UC 30,31,32 và 1 phần UC 29 | 70% | In Progress | 20140407 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/ThaoLTT
10 | 20140408 | ThaoLTT | Tạo Unit Test cho UC 29 và hoàn thiện Unit Test Case | 100% | Done | 20140408 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/ThaoLTT
11 | 20140408 | ThaoLTT | Review Unit Test | 100% | Done | 20140408 | 20140408 | N/A
12 | 20140408 | ThaoLTT | Coding cho UC29,UC30,UC31,UC32 | 15% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
13 | 20140410 | ThaoLTT | Tiếp tục code UC29,UC30,UC31,UC32 | 70% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
14 | 20140411 | ThaoLTT | Tiếp tục code UC29,UC30,UC31,UC32 | 85% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1

## VinhLT3
# | Ngày | Người đảm nhiệm | Nội dung công việc | Tiến độ | Status | Plan Start Date | Plan End Date | Note/Nơi lưu report
1 | 20140403 | VinhLT3 | Đọc Specs & Requirement | 100% | Done | 20140402 | 20140403 | N/A
2 | 20140403 | VinhLT3 | Log Q&A |  |  | 20140402 |  | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Q&A List/Fr-HN29n_Group1_Q-A list.xls
3 | 20140403 | VinhLT3 | Tạo screen desgin cho UC2.4,UC2.6,UC2.7 | 100% | Done | 20140403 | 20140403 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/ScreenDesign/ScreenDesign.xlsx
4 | 20140403 | VinhLT3 | Tạo database design cho UC2.4,UC2.6,UC2.7 | 90% | In Progress | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/DatabaseDiagram/G1_DatabaseDiagram.jpg
5 | 20140404 | VinhLT3 | Tạo class diagram cho UC 2.4, 2.6, 2.7 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/ClassDiagram/FR-HN29n_G1_ClassDiagram.xlsx
6 | 20140404 | VinhLT3 | Tạo sequencediagram cho UC 2.4, 2.6, 2.7 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/SequenceDiagram/FR-HN29n_G1_SequenceDiagram.xlsx
7 | 20140407 | VinhLT3 | Tạo Unit Test case cho UC 2.4, 2.6, 2.7 | 80% | In Progress | 20140407 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest
8 | 20140408 | VinhLT3 | Finish and review UT use case 2.4, 2.6, 2.7 | 100% | Done | 20140408 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest
9 | 20140408 | VinhLT3 | Design CSS, UI | 20% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
10 | 20140410 | VinhLT3 | Coding cho UC2.4,UC2.6 | 70% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
11 | 20140411 | VinhLT3 | Coding cho UC2.4,UC2.6,UC2.7 | 85% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
1
2
3
4
5
6
7
8
9

## HieuBV1
# | Ngày | Người đảm nhiệm | Nội dung công việc | Tiến độ | Status | Plan Start Date | Plan End Date | Note/Nơi lưu report
1 | 20140403 | HieuBV1 | Đọc Specs & Requirement | 100% | Done | 20140402 | 20140403 | N/A
2 | 20140403 | HieuBV1 | Log Q&A |  |  | 20140402 |  | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Q&A List/Fr-HN29n_Group1_Q-A list.xls
3 | 20140403 | HieuBV1 | Tạo screen desgin cho UC2.1,UC2.2,UC2.3 | 100% | Done | 20140403 | 20140403 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/ScreenDesign/ScreenDesign.xlsx
4 | 20140403 | HieuBV1 | Tạo database design cho UC2.1,UC2.2,UC2.3 | 60% | In Progress | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/DatabaseDiagram/G1_DatabaseDiagram.jpg
5 | 20140404 | HieuBV1 | Tạo class diagram cho UC 2.1, 2.2, 2.3 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/ClassDiagram/FR-HN29n_G1_ClassDiagram.xlsx
6 | 20140404 | HieuBV1 | Tạo sequencediagram cho UC 2.1, 2.2, 2.3 | 100% | Done | 20140404 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/SequenceDiagram/FR-HN29n_G1_SequenceDiagram.xlsx
7 | 20140407 | HieuBV1 | Tạo Unit Test Cho UC 2.1, 2.3 | 60% | In Progress | 20140407 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/HieuBV1
8 | 20140408 | HieuBV1 | Tạo Unit test cho UC2.2 và hoàn thiện Unit test | 100% | Done | 20140408 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/HieuBV1
9 | 20140408 | HieuBV1 | Review Unit Test | 100% | Done | 20140408 | 20140408 | N/A
10 | 20140408 | HieuBV1 | Coding cho trang UC2.1 | 20% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
11 | 20140410 | HieuBV1 | Hoàn thiện UC2.1 và tiếp tục code UC2.2 | 50% | In Progress | 20140410 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
| 20140411 | HieuBV1 | Hoàn thiện UC2.2 và tiếp tục code UC2.3 | 85% | In Progress | 20140411 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1

## DungVH4
# | Ngày | Người đảm nhiệm | Nội dung công việc | Tiến độ | Status | Plan Start Date | Plan End Date | Note/Nơi lưu report
1 | 20140403 | DungVH4 | Đọc Specs & Requirement | 100% | Done | 20140402 | 20140403 | N/A
2 | 20140403 | DungVH4 | Log Q&A |  |  | 20140402 |  | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Q&A List/Fr-HN29n_Group1_Q-A list.xls
3 | 20140403 | DungVH4 | Tạo screen desgin cho UC3,UC4 | 100% | Done | 20140403 | 20140403 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/ScreenDesign/ScreenDesign.xlsx
4 | 20140403 | DungVH4 | Tạo database design cho UC3,UC4 | 70% | In Progress | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/DatabaseDiagram/G1_DatabaseDiagram.jpg
5 | 20140404 | DungVH4 | Tạo class diagram cho UC3, UC4 | 100% | Done | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/ClassDiagram/FR-HN29n_G1_ClassDiagram.xlsx
6 | 20140404 | DungVH4 | Tạo sequence diagram cho UC3, UC4 | 100% | Done | 20140403 | 20140404 | https://10.16.102.18/svn/FRHN29n_G1/Wip/Docs/Diagram/SequenceDiagram/FR-HN29n_G1_SequenceDiagram.xlsx
7 | 20140407 | DungVH4 | Viết unit test case cho UC3, UC4 | 60% | In Progress | 20140407 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/DungVH4
8 | 20140408 | DungVH4 | Hoàn thành nốt và review unit test case cho UC3 và UC4 | 100% | Done | 20140407 | 20140408 | https://10.16.102.18/svn/FRHN29n_G1/Wip/UnitTest/DungVH4
9 | 20140408 | DungVH4 | Design CSS và UI | 20% | In Progress | 20140408 | 20140414
11 | 20140410 | DungVH4 | Coding cho UC3 và UC4 | 40% | In Progress | 20140408 | 20140414 | https://10.16.102.18/svn/FRHN29n_G1/Wip/LastestCode/G1
12 | 20140411 | DungVH4 | Coding cho UC3 và UC4 | 60% | In Progress | 20140408 | 20140414